UNOS 30 / 60 / 90 Day Commercial Growth Action Plan

Marketing + Sales + Philanthropy execution plan | Aligned to $10M 2026 qualified pipeline objective | Croom Lawrence / PredictCare.ai | July 2026 | Confidential draft for discussion

# 1. Executive objective

This 30/60/90 day plan translates the UNOS financial audit, OPO commercial growth plan, commercial tech stack roadmap, transplant database audit, and “What If” future use-case exploratory into a simple execution plan for the integrated Marketing + Sales + Philanthropy function.

The goal is to build a $10M qualified sales pipeline by the end of 2026 — not to claim $10M in recognized 2026 revenue. The plan is designed to produce quick wins, concrete account movement, executive proof, and a repeatable growth operating cadence.

# 2. Tick-and-tie to existing documents

| Source document | Key idea used here | Where it shows up in this 30/60/90 plan |
| --- | --- | --- |
| UNOS Financial Baseline / SWOT | FY2025 deficit ~$7.6M; revenue concentration; need mission-aligned commercial discipline | $10M pipeline objective, executive dashboard, weekly deal desk, board-ready proof |
| OPO Commercial Growth Plan | 55 OPOs, $10M qualified pipeline, 25–30 SQOs, 12–15 proposals, 4–6 pilots/diagnostics | 30/60/90 pipeline milestones and sales execution workstreams |
| Commercial Tech Stack Roadmap | One Brain, CRM discipline, agent fleet, meeting-to-action, pipeline hygiene, philanthropy engine | Operating system setup, agent deployment, weekly reporting, CRM governance |
| UNOS / OPTN Database Audit | Data assets can be packaged as governed intelligence products, not raw data | Offer architecture, OPO use cases, compliance language, product narrative |
| What If Future Use Case Exploratory | OPO Yield Intelligence, Nonuse Root Cause, Data Quality Copilot, DCD Expansion, Logistics, Equity | First 3 concept sheets, diagnostic offers, philanthropy / partner-funded initiatives |

# 3. North-star measurable outcomes

| Metric | 30 days | 60 days | 90 days / Q4 run-rate |
| --- | --- | --- | --- |
| OPO account coverage | 55/55 mapped and owned | 45+ engaged | 45+ active or nurtured |
| Tier 1 OPOs | Top 10–12 identified | 10+ executive meetings / active conversations | 5–7 qualified opportunities |
| Marketing-qualified accounts | 20–25 | 30–35 | 35+ |
| Sales-qualified opportunities | 8–10 | 18–22 | 25–30 |
| Proposals / scopes submitted | 2–4 | 7–9 | 12–15 |
| Qualified pipeline | $2.5M–$3.5M | $6M–$7.5M | $10M+ |
| Weighted pipeline | $500K–$1M | $1.5M–$2.25M | $2.5M–$3.5M |
| Signed diagnostics / pilots | 1–2 | 3–4 | 4–6 |
| Referenceable proof points | 0–1 in motion | 1–2 in motion | 2–3 in motion |
| Philanthropy / partner concept notes | 1–2 | 3–5 | $1M–$1.5M partner/grant pipeline |

# 4. 30-day plan: build the engine and create immediate proof

Theme: establish commercial control, map the market, launch the first OPO motion, and make the new growth thesis tangible.

| Workstream | Concrete actions | Owner | Output by day 30 | Success metric |
| --- | --- | --- | --- | --- |
| Revenue operations | Confirm CRM source of truth; define pipeline stages; create $10M dashboard; create weekly deal desk | CGO + RevOps | Pipeline governance SOP + dashboard v1 | Dashboard live; stage definitions approved |
| OPO account coverage | Map all ~55 OPOs; assign owners; tier top 20 by readiness, risk, relationship, and value | Sales + Strategy | OPO account map and tiering table | 55/55 mapped; top 20 prioritized |
| Sales quick wins | Draft and send first 20 executive OPO outreach emails; book first discovery meetings | CGO + Sales | Outreach library + meeting sequence | 8–10 meetings booked |
| Product packaging | Turn future use cases into three one-page concepts: OPO Yield Intelligence, Nonuse Root-Cause Dashboard, Data Quality Copilot | Product + Marketing | 3 customer-facing concept sheets | Ready for top 20 account conversations |
| Marketing foundation | Refresh UNOS portal materials; build OPO message architecture; launch 8-week content calendar | Marketing | Portal + message house + calendar | Materials live; first 4 content assets drafted |
| Philanthropy foundation | Create mission funding thesis and target list for equity, utilization, AI-for-good, and data modernization | Philanthropy + CGO | Top 25 donor/foundation/partner map | 25 prospects mapped; first 2 concept notes scoped |
| Tech stack / agents | Stand up meeting-to-action, account research, KPI digest, and pipeline hygiene agents | RevOps + Hermes-style operator | Agent workflow v1 | Weekly digest and stale-deal report running |
| Compliance | Approve language guardrails: no PHI, no selling data, human-governed decision support | Compliance + CGO | Claims and AI approval matrix | Guardrails embedded in templates |

## 30-day quick wins

First 20 OPO account briefs created.

First 20 executive outreach emails sent.

First 8–10 discovery meetings booked.

First 3 OPO solution concept sheets ready for customer conversations.

First weekly pipeline dashboard reviewed with leadership.

First philanthropy / partner-funded OPO improvement concept note drafted.

# 5. 60-day plan: convert interest into diagnostics and qualified pipeline

Theme: move from materials and outreach to active opportunities, diagnostics, proposals, and partner/foundation cultivation.

| Workstream | Concrete actions | Owner | Output by day 60 | Success metric |
| --- | --- | --- | --- | --- |
| Sales conversion | Run discovery with Tier 1/2 OPOs; offer diagnostic as conversion step; multi-thread each active account | CGO + Sales | Active opportunity list | 18–22 SQOs; 3+ contacts/account for active accounts |
| Diagnostic motion | Launch paid/sponsored OPO Performance Diagnostic for first accounts | Sales + Delivery | Diagnostic SOW + delivery plan | 3–4 diagnostics/pilots signed or in legal/procurement |
| Proposal factory | Build proposal kit: scope, price range, implementation plan, data governance note, ROI / mission rationale | Sales + Legal + Marketing | Proposal library | 7–9 proposals submitted |
| Marketing activation | Host OPO webinar/roundtable; launch self-assessment; start nurture sequence | Marketing | Webinar + self-assessment + nurture | 30–35 MQAs; 35 unique OPO accounts engaged |
| Product proof | Use meeting feedback to refine concept sheets and define “Command Center” pilot scope | Product + Sales | Pilot blueprint | 2–3 command-center candidates identified |
| Philanthropy / partners | Send 3–5 concept notes to foundations/partners aligned to equity, utilization, logistics, or AI-for-good | Philanthropy | Concept-note packet | $500K–$750K partner/grant pipeline identified |
| Tech stack / agents | Enable CRM write-back, meeting summaries, objection tracking, and weekly executive KPI digest | RevOps + AI operator | Growth OS v2 | 90%+ meetings summarized and logged within 24 hours |
| Governance | Run deal desk for every proposal; review compliance, pricing, delivery, and margin before submission | CGO + Legal + Finance | Deal desk minutes | 100% proposals reviewed before send |

## 60-day quick wins

18–22 sales-qualified opportunities in the funnel.

$6M–$7.5M qualified pipeline created.

7–9 proposals/scopes submitted.

3–4 diagnostics/pilots signed or in procurement/legal.

3–5 philanthropy/partner concept notes circulated.

First voice-of-customer objection library created.

# 6. 90-day plan: scale the cadence and prove the 2026 pipeline target

Theme: convert the strongest diagnostics and proposals into signed pilots, referenceable proof, and a $10M+ qualified pipeline.

| Workstream | Concrete actions | Owner | Output by day 90 | Success metric |
| --- | --- | --- | --- | --- |
| Pipeline scale | Advance Tier 1/2 opportunities; enforce next steps; prune no-chase accounts | CGO + Sales | Clean forecast and no-chase list | 25–30 SQOs; $10M+ qualified pipeline |
| Close pilots | Convert diagnostics into signed pilots/subscriptions/command-center scopes | Sales + Delivery | Signed pilots / SOWs | 4–6 paying pilots/diagnostics |
| Case-study proof | Turn early diagnostics into case-study-in-progress narratives | Marketing + Customer Success | 2–3 referenceable proof points in motion | 2–3 case studies or anonymized proof narratives |
| Executive reporting | Build board-ready growth page: pipeline, weighted forecast, mission proof, risks, next asks | CGO + Finance | Board / leadership report | $2.5M–$3.5M weighted pipeline |
| Philanthropy / partner pool | Convert concept notes into funded initiative pipeline | Philanthropy + CGO | Partner-funded OPO improvement pool | $1M–$1.5M partner/grant pipeline |
| Product roadmap | Decide which concepts become 2027 repeatable products | Product + CGO | 2027 product roadmap | Top 3 product bets approved |
| Tech stack hardening | Move from ad hoc agents to auditable recurring workflows | RevOps + IT + Compliance | Growth OS v3 | Weekly digest, CRM QA, meeting-to-action, and pipeline hygiene running reliably |
| Governance | Finalize AI/data/compliance operating guardrails for customer-facing products | Compliance + Legal | Governance checklist | Product claims and data-use risks reviewed |

## 90-day quick wins

$10M+ qualified OPO pipeline visible in CRM.

$2.5M–$3.5M weighted pipeline with stage confidence.

4–6 paying pilots/diagnostics signed or substantially through procurement.

12–15 proposals submitted.

2–3 proof narratives in motion.

Partner/philanthropy pipeline supporting equity, utilization, AI-for-good, or modernization.

# 7. Integrated weekly operating cadence

| Meeting | Frequency | Purpose | Required output |
| --- | --- | --- | --- |
| Growth stand-up | Weekly | Review movement across Marketing, Sales, Philanthropy, and product packaging | Top 10 opportunities, blockers, next actions |
| Deal desk | Weekly | Review pricing, scope, compliance, margin, delivery capacity, and legal risk | Approve / revise / no-chase decision |
| Pipeline hygiene review | Weekly | Clean stale opportunities, missing next steps, weak stage definitions | CRM cleanup list |
| Marketing performance review | Biweekly | Review content, webinar, self-assessment, and nurture conversion | Campaign improvement actions |
| Philanthropy / partner review | Biweekly | Review foundation, donor, and partner-funded initiative movement | Concept-note and relationship next steps |
| Executive review | Monthly | Summarize pipeline, weighted forecast, proof, risks, and asks | Board-ready growth page |

# 8. Simple role clarity

| Function | 30/60/90 responsibility | KPI owned |
| --- | --- | --- |
| CGO | Own strategy, whale accounts, deal desk, executive reporting, cross-functional alignment | $10M pipeline, proposals, weighted forecast |
| Sales | Own OPO account coverage, discovery, proposals, multi-threading, next steps | SQOs, meetings, proposals, closed pilots |
| Marketing | Own message architecture, content, portal, webinar, nurture, proof narratives | MQAs, engagement, meetings sourced, case studies |
| Philanthropy | Own mission funding thesis, donor/foundation/partner map, concept notes | Partner/grant pipeline, concept notes, donor meetings |
| RevOps | Own CRM, dashboards, stage hygiene, reporting, automation | Data quality, forecast accuracy, stale deal reduction |
| Product / Delivery | Own diagnostic scope, command-center package, delivery feasibility | Pilot design, time to first value, delivery margin |
| Compliance / Legal | Own claim review, data-use guardrails, contracting risk | 100% review of external claims/proposals above threshold |
| AI / Agent operator | Own meeting summaries, account briefs, KPI digests, pipeline hygiene, content drafts | Cycle time reduction, task completion, auditability |

# 9. Board / leadership narrative

In the first 90 days, UNOS can stand up a disciplined commercial operating system, map and engage the OPO market, convert its database and workflow expertise into customer-facing diagnostic offers, and build a $10M qualified pipeline without compromising mission, trust, or compliance.

The simple strategic story:

1. Financial audit: UNOS needs revenue diversification and operating leverage.

2. Database audit: UNOS has unique data and workflow assets that can become governed intelligence products.

3. What If exploratory: Those assets translate into concrete future solutions.

4. Tech stack roadmap: A One Brain + agent fleet can make the growth function faster and more accountable.

5. 30/60/90 plan: Execute the first OPO wedge with clear owners, metrics, proposals, pilots, and proof.

# 10. Language to use externally

“Qualified pipeline objective, not revenue-recognition promise”

“Mission-aligned performance improvement”

“Accreditation readiness and quality improvement”

“Permissioned, governed analytics”

“Human-governed decision support”

“Helping OPOs reduce burden and turn data into action”

“Responsible AI-readiness and technology maturity”

# 11. Language to avoid

“Selling the database”

“Monetizing patient data”

“AI replacing clinicians”

“Guaranteed outcomes”

“Unrestricted use of OPTN/UNet data”

“Move fast and break things”

# 12. Bottom line

This is intentionally simple: map the accounts, package the three highest-value OPO use cases, launch disciplined outreach, convert meetings into diagnostics, convert diagnostics into proposals and pilots, and report weekly against the $10M qualified-pipeline objective.

The plan is ambitious but achievable because it focuses senior time on the highest-value accounts, uses AI agents for repeatable execution, keeps compliance in the workflow, and turns existing UNOS data/workflow expertise into concrete customer-facing solutions.